ANNEX A

Project Design Document

LWU - APHEDA

Extension-‘Training for Employment and Poverty Reduction through the income generation for Women 2010-2013’

16 August, 2010

GENERAL PROJECT INFORMATION

1.1	Project Title, Location and Timing

| Project Name | Extension-Training for Employment and Poverty Reduction Through Income Generation for Women |
| --- | --- |
| Country, Region, Province, Specific Location | Lao PDR: Vientiane Capital, Luang Prabang, Xienkuang plus national structures |
| Expected Start-up Date Expected Finish Date Project Duration | 1 Sep 2010 31Aug 2013 3 year project |

  - Agency Details

| Sponsoring Australian NGO Name Principal Contact Officers | Union Aid Abroad - APHEDA Mr Phillip Hazelton Mekong Regional Manager Khampasong Siharath Lao PDR Country Manager |
| --- | --- |
| Delivery Organisations in Recipient Country | National Lao Women's Union (LWU) and three provincial branches: Vientiane Capital Women’s Union (VCWU), Xienkuang Women's Union (XKWU) and Luang Prabang Women’s Union (LPWU) |

2.	NEEDS ANALYSIS AND PROJECT DESIGN

2.1 	Brief Background to Situation

Through almost 10 years of this project the LWU partners have successfully established vocational training centres for the first time in Luang Prabang Province, Vientiane Capital and at the National LWU Training Centre.

The experience and skills developed by managers and trainers, the networks created with other centres and institutes nationally and regionally, the assets provided through infrastructure and equipment have combined to provide the Lao Women’s Union with both an effective new mechanism to contribute to both poverty alleviation in Lao PDR as well as career advancement and training opportunities for women generally.

The project evaluation completed in 2006, revealed encouraging outcomes in terms of poverty alleviation even in the early stages of the project, with an average 93% increase in income pre and post training for graduates. Most graduates are establishing micro enterprises and self-employment. Therefore they are not constrained by the sometimes limited full time employment opportunities in Lao PDR. A strong focus of the project has been capacity building of trainers and managers to assist longer term sustainability.

2.2 	Statement of Development Needs/Issues

This 3 year extension will

- provide an opportunity to assist poverty alleviation at a significant local level,

- continue to support capacity building of the vocational centres

- strengthen LWU in evaluation and monitoring

- shift the focus of the assistance to rural poor women as the extension will expand assistance to one new provincial women's union - Xien Kuang, scale down in Vientiane Capital and maintain support to Luang Prabang.

Key needs and issues for the extension period are as follows:

- Despite progress being made, there is still a need to improve financial sustainability of the centres by diversifying funding and support  base

- Continuing focus on improving quality of education through trainer skill improvement, expanding linkages with the national non-formal education system, further development and approval from Ministry of Education of curriculum for short courses and upgrade courses.

- Building capacity for the development of new courses based on market need.

- Expand project to another target province to access more poorest of the poor like Xienkuang province

2.3	How the Extension will address Development Needs/Issues

By addressing the training needs of poor communities, the project will continue to contribute towards development by improving access to education and skill opportunities for young women in particular.

Overall the 3 year extension will:

- Expand Voc. Education experience to another new target province to access more poorest of the poor

- Support improved quality of training offered by the centres,

- Target non-formal vocational training for poor and marginalised women,

- Support income generation and small business development for urban and rural poor and

- Contribute to national awareness of STD/HIV issues and other life skills for young people.

  - Project Design

    - Major Development Objectives

The major development objectives are:

- To build capacity of  LWU to deliver quality vocational training and good management practice

- Improve vocational skills, employment, micro-enterprise opportunities for poor women.

- To assist Vocational Centres to achieve a diversified funding base to strengthen longer term sustainability

Summary Log Frame

| Project Summary | Performance Indicators | Means/Sources of Verification | Risks & Assumptions |
| --- | --- | --- | --- |
| ##### Project Ext. Outcomes 1/ Poverty alleviation through vocational training, micro-enteprise dev. and food security opportunities for unskilled and semi-skilled poor women 2/ Increased capacity for training and project management by partners 3/Improved sustainability through increased quality of training and trialing of alternate funding sources for LWU centres 4) Establish and share experience on Voc. Education to new target province. | - No. women and men trained in vocational skills (>95% women) - Number of micro-enteprises operating/income level changes - selection procedures and participation rates by targeted disadvantaged groups in training - Number of curriculum approved by Ministry of Education - Number of alternative funding sources used to provide funding for LWU centres - >90% of trainees successfully trained (graduating) in each program; - continuation of training centres in training beyond this project - Share experience and resources from current LWU Voc. Centers. | - monitoring/reports by APHEDA Tech advisors and staff - monitoring/reports by partners - end of project evaluation | Potential Risks: Skills transferred to key staff lost to centres through Gov. transfers. Provincial Authorities don’t support as much as anticipated Assumptions: Lessons of last ten years incorporated in the next 3 year project current key staff remain with the project |

| Project Summary | Performance Indicators | Means of Verification | Risks & Important Assumptions |
| --- | --- | --- | --- |
| # Major Project Outputs 1.Signif.development in capacity of partner personnel and trainers - CLWU can be able to assess and strengthen leader capacity of provincial women union branches in 10 provinces. - 10 Managers upgrade skills on project management, accounting and English. - 24 trainers and assist. Trainers from vocational training centres upgraded as trainers - upgrade courses, handbooks, curriculum developed and trialed in Housekeeping, food processing/hospitality, HD and Tailoring - Train new trainers (15) on teaching methods and technical areas; HD, TL, food processing/hospitality and housekeeping. - Organizing donor meeting and Strategic Plan Developed for each Centre in year 2 to search for broader support. 2/ Training for targeted groups - 652 poor women and 20 poor men in vocational education for employment and income generation skills (7 subjects – Tailoring, Hairdressing, massage, embroidery, weaving, cooking/hospitality, housekeeping) - Additional 150 training places offered for fee paying students including for ex-trainees to do upgrade courses | - Target numbers of trainees successfully selected and trained - Trainers assessed as having skill levels to successfully provide quality training - >90% poor trainees accepted for training - Development of partner capacity in training. - number of courses undertaken - Strategic Plans completed by each centre | - Training centre records, project monitoring by partner and APHEDA personnel - Data collection and surveys of voc trainees - Field monitoring by partner personnel and APHEDA - Reports of national LWU - Results mid-term and final evaluation | Assumptions: personnel will make every effort to ensure that gender targets and criteria of disadvantage are met in selecting trainees, trainers. The training can be built up to be of a high standard, project participants will be selected against positive indications for success, e.g. interest, appropriate pond size and situation |

| ### Project Summary | Performance Indicators | Means/Sources of Verification/ | Risks & Important Assumptions |  |
| --- | --- | --- | --- | --- |
| # Major Project Inputs Resources - Technical Advisors (NFE-KM8+Thailand) in teaching methodology, technical, curriculum development - Funds for training, equipment, rebuilding and revolving loans - Australian TA/Regional manager. Local staff/equip - District and Province to provide land, buildings and management staff to centres - Australian TA/regional manager (2) - APHEDA office, vehicles, 3 local staff and equipment | - Timely placement of advisors and local office staff - Number of trainees by disadvantage group completing training - staff provided by Province - TOT courses completed successfully - Timely provision of funding - TA’s recruited and viewed as appropriate to needs | - All activities and performance indicators will be verified through on-going monitoring of the activities by the partner, APHEDA Laos-based personnel, APHEDA head office personnel, and through end of project participatory evaluation. | Risks as outlined above Assumptions which will minimize risks are: - that personnel appointed for training and project management are appropriate for the roles - that the training offered will be in demand from the proposed target communities - That TAs identified in first years are available in year 3. |  |

2.4.2	Project Design

This 3 year extension proposal is based on appraisal of direct requests from the national and provincial partner organisations. Inputs have been designed after detailed discussion with these partners, informed by the experience gained from 10 years implementation and the final evaluation.

Specifically it is planned to undertake from Sep 2010 till Aug 2013:

10 x three month courses of hairdressing, 11 x four month courses in tailoring, 3 x three month courses in food processing/hospitality, 2 x two week courses in food processing/cooking, 1 x  two week courses in handicrafts/souvenir,  3 x 2 months weaving/natural dye, 5 x 10-20 day courses in massage, 5 x 2 months courses in Embroidery, 2 x 10 day courses in Housekeeping and 1 x 10day course in Tourist guide.

In addition at least 2 x 10 days Training of Trainers in teaching method and technical skills appropriate to their subjects will be undertaken and upgrading capacity for centers’ managers and management teams on the subjects of Project Cycle Management, Accounting and English and other necessary an appropriated. Upgrade handbook and curriculum for Tailoring and hairdressing will be developed and piloted as short courses. Each centre will be required to further develop its income generating activities and planning through the development of a strategic plan incorporating alternative income and training options 2010-2013.

Counterpart inputs have also been designed to share risk, offset costs and provide enhanced opportunity for sustainability. The design also incorporates short inputs on STD/HIV, other life skills and marketing.

3. 	BUDGET DESIGN AND FINANCIAL ISSUES

3.1	Presentation of Budget (see Attachment 1)

| Activity Year | AusAID ANCP | APHEDA Counterpart | Other Donors | Total |
| --- | --- | --- | --- | --- |
| Year 1 | AUD 80,000 | AUD 34,206 |  | AUD 114,206 |
| Year 2 | AUD 80,000 | AUD 34,374 |  | AUD 114,374 |
| Year 3 | AUD 80,000 | AUD 33,618 |  | AUD 113,618 |
|  | Total |  |  | UAD 342,308 |

#### ATTACHMENT 1 :

PROPOSED BUDGET

Australian dollars by Activity

The total project budget is AUD 341,000 (approximately equivalent to USD 306,000 at exchange rate of 0.9/USD) Funds are sourced  from AusAID-ANCP 75%  and APHEDA member donations 25% .

Budget detail

| No. | Description | Total |
| --- | --- | --- |
|  | Activities LWU | AUD |
| 1 | Training Project management staff LWU centres | 19,424 |
| 2 | Upgrade technical skills of vocational trainers | 30,347 |
| 3 | Support equipment, materials and refurbishment | 18,255 |
| 4 | Collect data and assess achievement of LWU | 16,667 |
| 5 | Training places for 670 poor women | 109,430 |
| 6 | Evaluation and follow up of courses and trainees | 15,555 |
| 7 | Provide revolving loans | 10,000 |
| 8 | Support to Vocational centres utility costs | 12,853 |
| 9 | Support for Strategic planning | 10,000 |
|  | Personnel APHEDA |  |
|  | Local staff | 33,333 |
|  | International staff | 10,000 |
|  | International Short-Term Technical Support |  |
|  | Operational costs APHEDA |  |
|  | Procurement | 13,333 |
|  | Office | 26,666 |
|  | Other operational costs Monitoring and evaluation cost | 16,667 |
|  | Sub – total | AUD 342,308 |

Annex 1           Detailed Budget by Year

YEAR 1: Sep 2010 - Aug 2011

LWU partners (CLWU, LWUTC, VCWU, LPWU and XKWU)

| Activity | Units | ANCP/ APHEDA | Partner/target participants | Total USD | Total AUD |
| --- | --- | --- | --- | --- | --- |
| Activity 1 Managers and trainers’ capacity building and sustainability: - Project management (1) - Accounting training (1) - English - Review/project planning - Handbook upgrading (HD, TL, Massg) - Exchange visit to LPWU | 4p x 1 (t)=6 4p x 1 (t)=6 2 p 10 leaders +staff | 600x6 660x6 620 832 600 1,250 | VCWU, XK,LPWU, VCWU, XK, LPWU VCWU VCWU VCWU XKWU | 3,600 3,960 620 832 600 1,250 |  |
|  |  |  |  | 10,862 | 12068 |
| Activity 2 - Upgrade technical skills of vocational trainers - TOT (16 trainers) - Handbook upgrading (HD, TL, Massg) - HD-Technical training (3 m) - Hospitality upgrading (1 m) - TOT-elderly health care (1) - TOT-Child care (1) - TOT- postnatal for mother and child care (1) - Demonstrate teaching housekeeping curriculum (1) - Upgrade HD Training | 2 (new) trainers 2 5 trainers 5 trainers 5 trainers 15 trainees + 2 | 2855 700 1,000 683 1,500 800 700 1,300 700 | 4 LWU partners VCWU XKWU XKWU LWUTC LWUTC LWUTC LWUTC | 2855 700 1,000 683 1,500 800 700 1,300 700 |  |
|  |  |  |  | 10,238 | 11376 |
| Activity 3 - Materials, equipment, rehabilitation of facilities: - | Building renovate kitchen (1) +1 training room, training equip, | 4,324 | LPWU, LWUTC | 4,324 |  |
|  |  |  |  | 4,324 | 4804 |
| Activity 4 - Collect data and assess achievement of LWU | 3 Provinces: UDX, LNT, XK | 5,000 | CLWU | 5,000 |  |
|  |  |  |  | 5,000 | 5556 |
| Activity 5 - Training for poor women: - Hairdressing - Tailoring - Massage - Embroidery (2 months) - Life-skills, productive health, marketing - Food P and Hosp. | 76 trainees 36 trainees 62 trainees 20 trainees 25 | 2284+4,574+3,960 5,342+4,920 1,524+318 2,395 541+865 2784 | XK(16)VC(30),LP(30), LP(30),XK(16) VC(30), LP(32), LP(20), LP, VCWU | 10,817 10,262 1,842 2,395 1,406 2784 |  |
| Trained 194 trainees in year 1 |  | Sub-total |  | 29,506 | 32784 |
| Activity 6 - Evaluation and follow up of courses and trainees IMC Meeting (6 monthly) Tracer study post training etc |  | 2,000 | VCWU/LWU/LWUTC/XKWU/LPWU | 2,000 1,000 |  |
|  |  |  |  | 3,000 | 3333 |
| Activity 7 - Loan for graduated partners from 3 LWU Voc training centres |  | 3,000 |  | 3,000 |  |
|  |  |  |  | 3,000 | 3333 |
| Activity 8 - Support to LWU Centres Utility costs : telephone, electricity, stationery, fuel.. |  | 500+1,905+ 1,450 | XKWU, LPWU, VCWU | 3,855 |  |
|  |  |  |  | 3,855 | 4283 |
| Activity 9 Support for Strategic planning |  |  |  |  |  |
| Strategic Planning W'shop and activities |  | 3000 |  | 3000 |  |
|  |  |  |  | 3,000 | 3333 |
| Personnel |  |  |  |  |  |
| Country manager | 1 P/T | 7,000 |  | 7,000 |  |
| Technical Adviser | 1 P/T | 3,000 |  | 3,000 |  |
| Locally employed staff/trainers | 2 P/T | 3,000 |  | 3,000 |  |
|  |  |  |  | 13,000 | 14444 |
| Operational costs |  |  |  |  |  |
| Field office costs/communications |  | 5,000 + 4,000 | APHEDA Rent + Office supplies | 9,000 |  |
| Local transport/vehicle costs |  | 5000 | APHEDA | 5,000 |  |
| Utility: telephone, electricity, stationery, fuel.. |  | 3,000 | APHEDA | 3,000 |  |
|  |  |  |  | 17,000 | 18889 |
| Total in USD |  |  |  | 102,785 | 114,206 |

YEAR 2: Sep 2011 - Aug 2012

LWU partners (CLWU, LWUTC, VCWU, LPWU and XKWU)

| Activity | Units | ANCP/ APHEDA | Partner/target participants | Total USD | Total AUD |
| --- | --- | --- | --- | --- | --- |
| Activity 1 Managers and trainers’ capacity building and sustainability: - Workshop for developing teaching visual aid - Workshop on exchanging lessons [curriculum/handouts on food processing, hairdressing, tailoring, and housekeeper] - English trainig course | 2 | 3,000 2,500 620 | LWUTC LWUTC VCWU | 3,000 2,500 620 |  |
|  |  |  |  | 6,120 | 6800 |
| Activity 2 - Upgrade technical skills of vocational trainers - Upgrading massage trainer skills - English training course (2) - Upgrading trainers technical skills - House Keeper TOT |  | 1,000 620 3500 730 | LWUTC VCWU LPWU/VCWU/ LWUTC/XKWU XKWU | 1,000 620 3,500 730 |  |
|  |  |  |  | 5,850 | 6500 |
| Activity 3 - Materials, equipment, rehabilitation of facilities: -1 Zigzag - 1 Hair washing bed - Equipment for HD, housekeeper, hospitality - Renovate kitchen -Printing course materials/Curriculum et | 1 1 1 All courses | 64 62 1000 5,000 2,500 | VCWU VCWU XKWU XKWU | 64 62 1000 5,000 2,500 |  |
|  |  |  |  | 8,626 | 9584 |
| Activity 4 - Collect data and assess achievement of LWU | 3 Provinces: UDX, LNT, XK | 5,000 | CLWU | 5,000 |  |
|  |  |  |  | 5,000 | 5556 |
| Activity 5 - Training for poor women: - Tailoring(3 Courses) - Hairdressing (4 Courses) - Massage (2 C) - Embroidery (2 C) - Life-skills, productive health, marketing - Housekeeping training (1 C) - Three month courses of food processing/hospitality (2 C) | 15+32 15+30+10 15+20 20 10 50 | 2,620+5332 2100+4852+2700 360+1,597 4,850 300+270+541 2,000 5,400 | VCWU, LPWU VCWU, LPWU,XKWU VCWU, LPWU LPWU XKWU,VCWU, LPWU LWUTC XK |  |  |
| Trained 234 trainees in year 2 |  | Sub-total |  | 32,922 | 36,588 |
| Activity 6 - Evaluation and follow up of courses and trainees IMC Meeting (6 monthly) Tracer study post training etc |  | 3,000 | VCWU/LWU/LWUTC/XKWU/LPWU | 3,000 1,000 |  |
|  |  |  |  | 4,000 | 4444 |
| Activity 7 - Loan for graduated partners from 3 LWU Voc training centres |  | 3,000 |  | 3,000 |  |
|  |  |  |  | 3,000 | 3333 |
| Activity 8 - Support to LWU Centres Utility costs : telephone, electricity, stationery, fuel.. |  | 2,509+500+ 1,404 | XKWU, LPWU, VCWU | 4,413 |  |
|  |  |  |  | 4,413 | 4903 |
| Activity 9 Support for Strategic planning |  |  |  |  |  |
| Strategic Planning W'shop and activities |  |  |  | 3000 | 3333 |
| Personnel |  |  |  |  |  |
| Country manager | 1 P/T | 7,000 |  | 7,000 |  |
| Technical Adviser | 1 P/T | 3,000 |  | 3,000 |  |
| Locally employed staff/trainers | 2 P/T | 3,000 |  | 3,000 |  |
|  |  |  |  | 13,000 | 14444 |
| Operational costs |  |  |  |  |  |
| Field office costs/communications |  | 5,000 + 4,000 | APHEDA Rent + Office supplies | 9,000 |  |
| Local transport/vehicle costs |  | 5000 | APHEDA | 5,000 |  |
| Utility: telephone, electricity, stationery, fuel.. |  | 3,000 | APHEDA | 3,000 |  |
|  |  |  |  | 17,000 | 18889 |
| Total in USD |  |  |  | 102931 | 114,374 |

YEAR 3: Sep 2012 - Aug 2013

LWU partners (CLWU, LWUTC, VCWU, LPWU and XKWU)

| Activity | Units | ANCP/ APHEDA | Partner/target participants | Total USD | Total AUD |
| --- | --- | --- | --- | --- | --- |
| Activity 1 Managers and trainers’ capacity building and sustainability: - English training course (2) |  | 500 | VCWU | 500 |  |
|  |  |  |  | 500 | 556 |
| Activity 2 - Upgrade technical skills of vocational trainers - Upgrading TL trainer skills - Upgrading food processing trainer skills - Upgrading housekeeper trainer skills - Upgrading trainers skills (HD,TL) - Upgrade trainers skills | 1 2 2 2 4 | 1,000 1,500 1,500 3,000 2,234 2,000 | XKWU LWUTC LWUTC LWUTC LPWU All centres |  |  |
|  |  |  |  | 11,224 | 12,471 |
| Activity 3 - Materials, equipment, rehabilitation of facilities: - Buying teaching equipment food processing - Industrial sewing machine, button pump, Zigzag, Washing machine, Iron |  | 2,000 1,480 | LWUTC VCWU | 2,000 1,480 |  |
|  |  |  |  | 3,480 | 3867 |
| Activity 4 - Collect data and assess achievement of LWU | 3 Provinces: UDX, LNT, XK | 5,000 | CLWU | 5,000 |  |
|  |  |  |  | 5,000 | 5556 |
| Activity 5 - Training for poor women: - Tailoring/Souvenir (1 Courses) - Weaving/natural dye (3 C) - Tailoring (4 C) - One and half month-Food processing/hospitality (1) - Hairdressing (3 Courses) - Massage (1 C) - Embroidery (2 C) - Catfish and loan (1 c) - Tourist guide - Life-skills, productive health, marketing | 15 60 15+32+6 +25 30+10 20 20 20 15 | 3,878 4,878 2100,5068, 2594 3,902 4224+ 2284 1,522 2,334 1567 505 168+541+488 | XKWU XKWU VCWU,LPWU, XKWU XKWU LPWU+XKWU LPWU LPWU LPWU LPWU VCWU,LPWU,XKWU |  |  |
| Trained 244 in Year 3 |  | Sub-total |  | 36,053 | 40,058 |
| Activity 6 - Evaluation and follow up of courses and trainees IMC Meeting (6 monthly) Final Evaluation |  | 2,000 | VCWU/LWU/LWUTC/XKWU/LPWU | 2,000 5,000 |  |
|  |  |  |  | 7,000 | 7778 |
| Activity 7 - Loan for graduated partners from 3 LWU Voc training centres |  | 3,000 |  | 3,000 |  |
|  |  |  |  | 3,000 | 3333 |
| Activity 8 - Support to LWU Centres Utility costs : telephone, electricity, stationery, fuel.. |  |  | XKWU, LPWU, VCWU | 3,300 |  |
|  |  |  |  | 3,300 | 3333 |
| Activity 9 Support for Strategic planning |  |  |  |  |  |
| Strategic Planning W'shop and activities |  |  | All partners | 3,000 |  |
|  |  |  |  | 3,000 | 3333 |
| Personnel |  |  |  |  |  |
| Country manager | 1 P/T | 7,000 |  | 7,000 |  |
| Technical Adviser | 1 P/T | 3,000 |  | 3,000 |  |
| Locally employed staff/trainers | 2 P/T | 3,000 |  | 3,000 |  |
|  |  |  |  | 13,000 | 14444 |
| Operational costs |  |  |  |  |  |
| Field office costs/communications |  | 5,000 + 4,000 | APHEDA Rent + Office supplies | 9,000 |  |
| Local transport/vehicle costs |  | 5,000 | APHEDA | 5,000 |  |
| Utility: telephone, electricity, stationery, fuel.. |  | 3,000 | APHEDA | 3,000 |  |
|  |  |  |  | 17,000 | 18889 |
| Total in USD |  |  |  | 102,257 | 113,618 |

## ATTACHMENT 2:  GENDER AND DEVELOPMENT MARKERS

|  |  | ## Yes/No | ## Comments |
| --- | --- | --- | --- |
| ## Q1 | Is the promotion of equality between women and men the main objective of the whole activity? (principal) ## The activity may target women specifically, men specifically or both women and men as long as the main objective is the promotion of equality between women and men. For example, support to legal literacy for women, or support to male networks against gender violence. Note: an activity such as a maternal health project would qualify for this marker. | ## No | ## While the training of women constitutes a significant element of this project, and much of the training is conducted by women's agencies, the project’s primary objective is to meet the vocational and technical training needs of poor rural and urban communities. |
| ## Q2 | Is promoting equality between women and men an objective of one or more components of the activity? (significant) Answer ‘yes” if one of the components has an objective which promotes equality between women and men. The objective may target women specifically, men specifically or women and men, for example, women’s literacy activities within a forestry project. | ## Yes |  |
| ## Q3 | Will gender sensitive consultation be incorporated into the activity? Answer ‘yes’ if systematic gender consultation with local people has been or will be part of the activity. This involves having a dialogue with both women and men on their perceptions and priorities, and making sure the views of both are made visible in the planning process. For example, consulting with both women and men in a micro-financing activity which mainly targets women, or women and men in an infrastructure activity such as road building. | ## Yes |  |
| ## Q4 | Will there be strategies to help overcome identified barriers to full participation of women and men? Answer ‘yes’ if specific barriers to participation have been or will be identified through gender analysis, and strategies to help overcome these barriers have been or will be designed. Gender analysis involves examining the different roles and responsibilities of women and men. | ## Yes |  |
| ## Q5 | Will there be strategies to help promote equitable participation of women and men in decision making roles? Answer ‘yes’ if steps are being taken to improve gender equality in decision-making. This does not necessarily mean 50% women and 50% men. | ## Yes |  |
| ## Q6 | Will there be gender sensitive indicators in place for monitoring and evaluation? ## Such gender sensitive indicators will measure the positive and negative consequences of the activity for women and men. Indicators may be quantitative or qualitative. | ## Yes | ## A series of performance indicators have been formulated, enabling project outcomes and outputs to be disaggregated by gender. |
| ## Q7 | ## Will the budget include an allocation for specific activities promoting gender equality? Answer ‘yes’ if there is a budget allocation for specific activities that have a main objective of promoting equality between women and men. Enter an estimated percentage in the percentage of budget box. | ## No | ## Percentage of Budget % |

##### ATTACHMENT 3:

##### ENVIRONMENTAL MARKERS

|  |  | Yes/No |
| --- | --- | --- |
| Q1 | Is this activity occurring in an environmentally sensitive location or sector? | No |
| Q2 | If the answer to question 1 is YES, the environmental impact of the activity may be direct or indirect. If the impact is direct, indicate YES. If indirect, indicate NO. |  |
| Q3 | Does this activity have the environment as a specific objective? | No |
| Q4 | Has environmental monitoring/reporting been built into the project design? | No |
|  | If YES describe the monitoring/reporting arrangements: |  |
| Q5 | Is this activity relevant to international environment conventions? If YES please indicate which conventions are relevant: | No |
|  | Percentage of budget directly supporting environment objectives. | 0% |

OTHER MARKERS

|  |  | Yes/No |
| --- | --- | --- |
| Q1 | Does the activity promote human rights? | Yes |
| Q2 | Has the impact on health been considered? | Yes |
| Q3 | Has the population checklist been completed? | Yes |

ATTACHMENT 4:

##### DAC SECTOR CODE CHECKLIST

Organisation: 	APHEDA

Activity Title: 	Extension-Training for Employment and Poverty reduction

for women 2010-2013

Scheme/CDC Reference: 	 AUSTRALIAN NGO/ANCP

###### DAC Sector Codes

| DAC Code (Five Digit) | Description | Class (One Primary and up to nine Secondary) | Impact (High/ Medium/Low) |
| --- | --- | --- | --- |
| 11330 | Vocational training | Primary | High |
| 42010 | Women in Development | Secondary | High |